## T2 sin SCRUM
Employee | Task | Date | Duration
Rodrigo | Concept | 2021-02-22 09:00 | 8
Rodrigo | Environmental Design | 2021-02-23 09:00 | 10
Rodrigo | Character Design | 2021-02-24 11:00 | 7
Rodrigo | Level Design | 2021-02-25 10:00 | 15
Sergio | Music Aligment | 2021-02-23 09:00 | 14
Sergio | Music Late Motifs | 2021-02-24 15:00 | 10
Arturo | Combat Programming | 2021-02-23 09:00 | 10
Arturo | World Programming | 2021-02-24 11:00 | 7
Arturo | Inventory Programming | 2021-02-25 10:00 | 6
Sergio | Music Testing | 2021-02-26 09:00 | 4
Arturo | Programming Testing | 2021-02-25 16:00 | 8
Rodrigo | Design Testing | 2021-03-01 09:00 | 6
Rodrigo | Release | 2021-03-01 15:00 | 2
- | Finish | 2021-03-01 17:00 | -

## SCRUM Completo T1
Employee | Task | Date | Duration
Rodrigo | Concept | 2021-02-22 09:00 | 8
All employees | Daily SCRUM | 2021-02-22 11:00 | 1
Arturo | Design | 2021-02-23 10:00 | 10
All employees | Daily SCRUM | 2021-02-23 11:00 | 1
All employees | Daily SCRUM | 2021-02-24 11:00 | 1
Sergio | Validation | 2021-02-24 14:00 | 5
All employees | Daily SCRUM | 2021-02-25 11:00 | 1
Arturo | Implementation | 2021-02-25 12:00 | 20
All employees | Daily SCRUM | 2021-02-26 11:00 | 1
All employees | Daily SCRUM | 2021-03-01 11:00 | 1
Arturo | Verification | 2021-03-02 10:00 | 5
All employees | Daily SCRUM | 2021-03-02 11:00 | 1
Rodrigo | Testing | 2021-03-02 16:00 | 8
All employees | Daily SCRUM | 2021-03-03 11:00 | 1
Rodrigo | Release | 2021-03-04 09:00 | 6
All employees | Daily SCRUM | 2021-03-04 11:00 | 1
- | Finish | 2021-03-04 16:00 | -

## SCRUM Completo T2
Employee | Task | Date | Duration
Rodrigo | Concept |  | 8
All employees | Daily SCRUM | 2021-02-22 11:00 | 1
Rodrigo | Environmental Design | 2021-02-23 10:00 | 10
Sergio | Music Aligment | 2021-02-23 10:00 | 14
Arturo | Combat Programming | 2021-02-23 10:00 | 10
All employees | Daily SCRUM | 2021-02-23 11:00 | 1
All employees | Daily SCRUM | 2021-02-24 11:00 | 1
Rodrigo | Character Design | 2021-02-24 14:00 | 7
Arturo | World Programming | 2021-02-24 14:00 | 7
Sergio | Music Late Motifs | 2021-02-25 10:00 | 10
All employees | Daily SCRUM | 2021-02-25 11:00 | 1
Rodrigo | Level Design | 2021-02-25 14:00 | 15
Arturo | Inventory Programming | 2021-02-25 14:00 | 6
All employees | Daily SCRUM | 2021-02-26 11:00 | 1
Arturo | Programming Testing | 2021-02-26 13:00 | 8
Sergio | Music Testing | 2021-02-26 14:00 | 4
All employees | Daily SCRUM | 2021-03-01 11:00 | 1
Rodrigo | Design Testing | 2021-03-01 15:00 | 6
All employees | Daily SCRUM | 2021-03-02 11:00 | 1
Rodrigo | Release | 2021-03-02 14:00 | 2
- | Finish | 2021-03-02 16:00 | -

## SCRUM Completo T3
Employee | Task | Date | Duration
Rodrigo | Concept | 2021-02-22 09:00 | 8
All employees | Daily SCRUM | 2021-02-22 11:00 | 1
Rodrigo | Environmental Design | 2021-02-23 10:00 | 10
Sergio | Music Aligment | 2021-02-23 10:00 | 14
Arturo | World Programming | 2021-02-23 10:00 | 7
All employees | Daily SCRUM | 2021-02-23 11:00 | 1
Arturo | Inventory Programming | 2021-02-24 10:00 | 6
All employees | Daily SCRUM | 2021-02-24 11:00 | 1
Rodrigo | Character Design | 2021-02-24 14:00 | 7
Sergio | Music Late Motifs | 2021-02-25 10:00 | 10
All employees | Daily SCRUM | 2021-02-25 11:00 | 1
Rodrigo | Level Design | 2021-02-25 14:00 | 15
All employees | Daily SCRUM | 2021-02-26 11:00 | 1
Sergio | Music Testing | 2021-02-26 14:00 | 4
All employees | Daily SCRUM | 2021-03-01 11:00 | 1
Arturo | Combat Programming | 2021-03-01 15:00 | 10
Rodrigo | Design Testing | 2021-03-01 15:00 | 6
All employees | Daily SCRUM | 2021-03-02 11:00 | 1
Arturo | Programming Testing | 2021-03-03 10:00 | 8
All employees | Daily SCRUM | 2021-03-03 11:00 | 1
All employees | Daily SCRUM | 2021-03-04 11:00 | 1
Rodrigo | Release | 2021-03-04 12:00 | 2
- | Finish | 2021-03-04 14:00 | -