## Tasks
Name | Duration | Compatibility | Dependencies
Concept | 8 | CEO | -
Environmental Design | 10 | Programmer | Concept
Character Design | 9 | Designer | Concept
Level Design | 15 | Designer | Concept
Music Aligment | 18 | Designer | Concept
Music Late Motifs | 14 | Designer | Concept
Combat Programming | 15 | Programmer | Music Late Motifs ¦ Level Design
World Programming | 10 | Programmer | Concept
Inventory Programming | 10 | Programmer | Concept
Music Testing | 7 | Programmer | Music Late Motifs
Programming Testing | 10 | Programmer | Inventory Programming
Design Testing | 12 | Programmer | Level Design
Legal Preparation | 15 | Lawyer | Concept
Copyright Research | 7 | Lawyer | Concept
Patent Infrigement | 8 | Lawyer | Concept
IP Registration | 12 | Lawyer | Concept
Competition | 6 | Marketing | Concept
Advertisements | 15 | Marketing | Concept
Influencer Contracts | 20 | Marketing | Concept
IRPF Management | 10 | RRHH | SS Contratcs
SS Contracts | 10 | RRHH | Concept
Expansion Investigation | 8 | RRHH | Concept
Monthly Expenditure | 7 | Accounting | Concept
Investments Payoff | 21 | Accounting | Concept
Future Viability | 10 | Accounting | Concept